## Sheet1
Task | Description | Priority | Status | Assigned | Start Date | Due Date
Project Initialization | Understand Project overview and goals | P1 | Completed | Atul Kumar | 2024-08-22 | 2024-08-23
| make list of output requirement | P1 | Completed | Atul Kumar | 2024-08-22 | 2024-08-23
| Set Database Structure | P1 | Completed | Atul Kumar | 2024-08-22 | 2024-08-23
| Set up Git repository, initialize a new Spring Boot project with necessary dependencies, | P1 | Completed | Atul Kumar | 2024-08-22 | 2024-08-23
Service Microservice | Set up microservice, define entities, and perform CRUD operations. | P1 | Completed | Atul Kumar | 2024-08-23 | 2024-08-24
Staff Microservice Setup | Set up the microservice, define entities, and perform CRUD operations. | P1 | Completed | Atul Kumar | 2024-08-24 | 2024-08-25
Customer Microservice Setup | Set up the microservice, define entities, and perform CRUD operations. | P1 | Completed | Atul Kumar | 2024-08-25 | 2024-08-26
Booking Microservice Setup | Set up the microservice and perform required operations. | P1 | Completed | Atul Kumar | 2024-08-26 | 2024-08-27
API Gateway Setup | Set up the API gateway and configure routes for microservices. | P1 | Completed | Atul Kumar | 2024-08-27 | 2024-08-28
Service Registry | Set up the Service Registry to connect all the services together | P1 | Completed | Atul Kumar | 2024-08-27 | 2024-08-28
Authentication Implementation | Implement authentication using Spring Security. | P1 | Completed | Atul Kumar | 2024-08-28 | 2024-08-30
Exception Handling | Implement global exception handling across all microservices. | P1 | Completed | Atul Kumar | 2024-08-28 | 2024-08-30
Testing (JUnit) | Write and run JUnit tests for each microservice to ensure functionality. | P1 | Completed | Atul Kumar | 2024-08-28 | 2024-08-30
Final Project Setup | Finalize all implementations and make any necessary adjustments or improvements. | P1 | Completed | Atul Kumar | 2024-08-28 | 2024-08-30
Presentation Preparation | Create a PowerPoint presentation and address any remaining tasks. | P1 | Completed | Atul Kumar | 2024-08-28 | 2024-08-30